## Phase 3
| UNIFORM INVOICE TRACKING SPREADSHEET FOR: DATE: | City of Harlowton Phase 3 Water System Improvements | [8 empty] | Date: |  | 2019-01-09 16:08
| Vendor's Name | Invoice or Pay Estimate Number | Invoice Date or Time Period Covered | Total Amount of Invoice | Warrant Number | Date Paid |  |  | Funding Source, Amount Expended, Drawdown Number | [9 empty] | Total Amount Paid This Invoice
IT# | [6 empty] | TSEP | # | CBDG | # | SRF A Loan | # | SRF B Loan |  | WRDA (Section 595) |  | Local
1 | Great West Engineering (Preliminary Design Phase) | 14225 | 2015-11-24 | 17612.97 | [8 empty] | 17613 | 1 |  |  |  |  | 17613
2 | Great West Engineering (Grant Administration) | 14226 | 2015-11-24 | 1620.25 | [8 empty] | 1620 | 1 |  |  |  |  | 1620
3 | Great West Engineering (Grant Administration) | 14394 | 2015-12-22 | 1055.75 | [8 empty] | 1056 | 1 |  |  |  |  | 1056
4 | Great West Engineering (Preliminary Design Phase) | 14395 | 2015-12-22 | 20914.5 | [8 empty] | 20915 | 1 |  |  |  |  | 20915
5 | Great West Engineering (Grant Administration) | 14451 | 2016-01-20 | 1213.75 | [8 empty] | 1214 | 1 |  |  |  |  | 1214
6 | Great West Engineering (Preliminary Design Phase) | 14452 | 2016-01-20 | 26077 | [8 empty] | 26077 | 1 |  |  |  |  | 26077
7 | Great West Engineering (Preliminary Design Phase) | 14557 | 2016-02-16 | 17303 | [8 empty] | 17303 | 1 |  |  |  |  | 17303
8 | Great West Engineering (Grant Administration) | 14558 | 2016-02-16 | 3015.75 | [8 empty] | 3016 | 1 |  |  |  |  | 3016
9 | Great West Engineering (Preliminary Design Phase) | 14650 | 2016-03-22 | 23957.05 | [8 empty] | 23957 | 1 |  |  |  |  | 23957
10 | Great West Engineering (Final Design Phase) | 14650 | 2016-03-22 | 1792.35 | [8 empty] | 1792 | 1 |  |  |  |  | 1792
11 | Great West Engineering (Phase 3A - Grant Administration) | 14651 | 2016-03-22 | 3839.5 | [8 empty] | 3840 | 1 |  |  |  |  | 3840
12 | Great West Engineering (Phase 3A - Preliminary Design Phase) | 14776 | 2016-04-21 | 1805.5 | [8 empty] | 1806 | 1 |  |  |  |  | 1806
13 | Great West Engineering (Phase 3A - Final Design Phase) | 14776 | 2016-04-21 | 7269.5 | [8 empty] | 7270 | 1 |  |  |  |  | 7270
14 | Great West Engineering (Phase 3A - Bidding) | 14776 | 2016-04-21 | 4251.57 | [8 empty] | 4252 | 1 |  |  |  |  | 4252
15 | Great West Engineering (Phase 3A - Grant Administration) | 14777 | 2016-04-21 | 1194.6 | [8 empty] | 1195 | 1 |  |  |  |  | 1195
16 | Great West Engineering (Phase 3A - Grant Administration) | 14929 | 2016-05-25 | 1276.5 | [6 empty] | 1277 | 1 | [6 empty] | 1277
17 | Great West Engineering (Phase 3A - Final Design Phase) | 14930 | 2016-05-25 | 5102.01 | [6 empty] | 5102 | 1 | [6 empty] | 5102
18 | Great West Engineering (Phase 3A - Bidding) | 14930 | 2016-05-25 | 5764.19 | [6 empty] | 5764 | 1 | [6 empty] | 5764
19 | Great West Engineering (Phase 3A - Final Design Phase) | 15010 | 2016-06-21 | 2449.27 | [6 empty] | 2449 | 1 | [6 empty] | 2449
20 | Great West Engineering (Phase 3A - Bidding) | 15010 | 2016-06-21 | 84.26 | [6 empty] | 84 | 1 | [6 empty] | 84
21 | Great West Engineering (Construction Management) | 15010 | 2016-06-21 | 5672.97 | [6 empty] | 5673 | 1 | [6 empty] | 5673
22 | Great West Engineering (Resident Project Representative) | 15011 | 2016-06-21 | 2166.2 | [6 empty] | 2166 | 1 | [6 empty] | 2166
23 | Great West Engineering (Phase 3A - Grant Administration) | 15013 | 2016-06-21 | 1552 | [6 empty] | 1552 | 1 | [6 empty] | 1552
24 | Battle Ridge Builders, LLC | 1 | 2016-06-29 | 282992.18 |  |  |  |  | 170436.18 | 1 | 112556 | 1 | [6 empty] | 282992.18
25 | Mahurin Excavating & Drilling (South Well Rehab) | 1 | 2016-06-09 | 19855 | [6 empty] | 19855 | 2 | [6 empty] | 19855
26 | Jeff's Electrical Service (South Well Rehab) | 1010 | 2016-06-19 | 602.75 | [6 empty] | 603 | 2 | [6 empty] | 603
27 | Ferguson Waterworks (South Well Rehab) | 635796 | 2016-06-22 | 1138.6 | [6 empty] | 1139 | 2 | [6 empty] | 1139
28 | Ferguson Waterworks (South Well Rehab) | 635795 | 2016-06-24 | 2497.39 | [6 empty] | 2497 | 2 | [6 empty] | 2497
29 | Jeff's Electrical Service (South Well Rehab) | 1021 | 2016-06-28 | 4370 | [6 empty] | 4370 | 2 | [6 empty] | 4370
30 | Jeff's Electrical Service (South Well Rehab) | 1027 | 2016-07-01 | 210 | [6 empty] | 210 | 2 | [6 empty] | 210
31 | SRF Reserve B Loan | 1 | 2016-07-26 | 5072 | [8 empty] | 5072 | 1 |  |  |  |  | 5072
32 | City's Payback of SRF reserve funds (Miscellaneous Expense on Disbursement Report) | 1 | 2016-07-26 | 25468 | [6 empty] | 25468 | 1 | [6 empty] | 25468
33 | US Bank Interest Charge for BAN | 1 | 2016-07-26 | 538.21 | [8 empty] | 538.21 | 1 |  |  |  |  | 538.21
34 | Great West Engineering (Phase 3A - Preliminary Design Phase) | 1 | 2016-07-19 | 53.5 | [6 empty] | 54 | 2 | [6 empty] | 54
35 | Great West Engineering (Phase 3A - Final Design Phase) | 15119 | 2016-07-19 | 7715.62 | [6 empty] | 7716 | 2 | [6 empty] | 7716
36 | Great West Engineering (Construction Management) | 15119 | 7/19/216 | 7053.62 | [6 empty] | 7054 | 2 | [6 empty] | 7054
37 | Great West Engineering (Resident Project Representative) | 15119 | 2016-07-19 | 21866.42 | [6 empty] | 21866 | 2 | [6 empty] | 21866
38 | Great West Engineering (Phase 3A - Grant Administration) | 15116 | 2016-07-19 | 1605 | [6 empty] | 1605 | 2 | [6 empty] | 1605
39 | Battle Ridge Builders, LLC | 2 | 2016-08-01 | 200556.04 |  |  |  |  | 200556.04 | 2 | [8 empty] | 200556.04
40 | Wilting Plumbing and Heating | 1 | 2016-06-01 | 565.25 | [6 empty] | 565 | 2 | [6 empty] | 565
41 | Great West Engineering (Phase 3A - Final Design Phase) | 15226 | 2016-08-29 | 3265.5 | [6 empty] | 3266 | 3 | [6 empty] | 3266
42 | Great West Engineering (Construction Management) | 15226 | 2016-08-29 | 9876.38 | [6 empty] | 9876 | 3 | [6 empty] | 9876
43 | Great West Engineering (Resident Project Representative) | 15226 | 2016-08-29 | 29798.98 | [6 empty] | 29799 | 3 | [6 empty] | 29799
44 | Great West Engineering (Phase 3A - Grant Administration) | 15226 | 2016-08-29 | 2354 | [6 empty] | 2354 | 3 | [6 empty] | 2354
45 | Northwest Pipe Fitting (Water Meters) | 1680109-1 | 2016-08-23 | 3999.76 | [8 empty] | 1000 | 2 | 2999.82 | 1 |  |  | 3999.82
46 | Northwest Pipe Fitting (Water Meters) | 1680109-1 | 2016-08-29 | 76467.62 | [8 empty] | 19117 | 2 | 57350.62 | 1 |  |  | 76467.62
47 | Battle Ridge Builders, LLC | 3 | 2016-09-01 | 193881.7 |  |  | 153536.7 | 1 |  |  | 40345 | 3 | [6 empty] | 193881.7
48 | SRF Reserve B Loan | 2 | 2016-09-14 | 764.45 | [8 empty] | 764 | 2 |  |  |  |  | 764
49 | Dorsey & Whitney | 3297771 | 2016-07-26 | 10000 | [6 empty] | 5000 | 4 | 5000 | 3 |  |  |  |  | 10000
50 | SRF Reserve B Loan | 3 | 2016-09-16 | 190 | [8 empty] | 190 | 3 |  |  |  |  | 190
51 | Rounding adjustment (Per Rob Ashton) | [11 empty] | -0.21
52 | TSEP Grant Administration Training Expenses | 1 | 2015-07-08 | 262.73 |  |  | 262.73 | 2 | [10 empty] | 262.73
53 | CDBG Grant Administration Training Expenses | 1 | 2015-11-19 | 281.34 |  |  |  |  | 281.34 | 3 | [8 empty] | 281.34
54 | Northwest Pipe Fitting (Water Meters) | 1700083 | 2016-09-19 | 881.25 | [8 empty] | 220 | 4 | 661.25 | 2 |  |  | 881.25
56 | Great West Engineering (Thompson Well Replacement) | 15384 | 2016-09-23 | 462 | [8 empty] | 462 | 4 |  |  |  |  | 462
57 | Great West Engineering (Phase 3A - Final Design Phase) | 15384 | 2016-09-23 | 242 | [6 empty] | 242 | 5 | [6 empty] | 242
58 | Great West Engineering (Construction Management) | 15384 | 2016-09-23 | 8529.15 | [6 empty] | 8529 | 5 | [6 empty] | 8529
59.5 | Great West Engineering (Resident Project Representative) | 15384 | 2016-09-23 | 22004.21 | [6 empty] | 22004 | 5 | [6 empty] | 22004
60.8 | Great West Engineering (Grant Administration) | 15324 | 2016-09-20 | 2654.55 | [8 empty] | 2655 | 4 |  |  |  |  | 2655
62.1 | Battle Ridge Builders, LLC | 4 | 2016-09-30 | 297730.86 |  |  | 40232.42 | 2 | 69726.44 | 3 |  |  | 83522 | 4 | 104250 | 2 |  |  | 297730.86
63.4 | SRF Reserve B Loan | 4 | 2016-10-05 | 3300.64 | [8 empty] | 3301 | 4 |  |  |  |  | 3301
64.7 | Great West Engineering (Grant Writing Services) | 14931 | 2016-05-25 | 9406.96 | [8 empty] | 9405 | 5 |  |  |  |  | 9405
66 | Northwest Pipe Fitting (Water Project) | 1700083 | 2016-09-19 | 1303.44 |  |  | 326 | 3 | [6 empty] | 977.44 | 3 |  |  | 1303.44
67.3 | DIS Tech * | 30372 | 2016-10-06 | 948.6 |  |  | 948.6 | 3 | [10 empty] | 948.6
68.6 | Northwest Pipe Fitting (Water Meters) | 1700084 | 2016-09-19 | 74.65 | [8 empty] | 19 | 5 | 55.65 | 3 |  |  | 74.65
69.9 | Northwest Pipe Fitting | 1700093 | 2016-09-19 | 314.81 |  |  | 79 | 3 | [6 empty] | 235.81 | 3 |  |  | 314.81
71.2 | Northwest Pipe Fitting | 1700738 | 2016-09-26 | 172.54 |  |  | 43 | 3 | [6 empty] | 129.54 | 3 |  |  | 172.54
72.5 | Northwest Pipe Fitting | 1700753 | 2016-09-26 | 87.7 |  |  | 22 | 3 | [6 empty] | 65.7 | 3 |  |  | 87.7
73.8 | Northwest Pipe Fitting (Water Meters) | 1700775 | 2016-09-26 | 2043.16 | [8 empty] | 511 | 5 | 1532.16 | 3 |  |  | 2043.16
75.1 | Liquid Engineering | 15150 | 2016-10-12 | 4325 | [8 empty] | 4325 | 5 |  |  |  |  | 4325
76.4 | Liquid Engineering | 15156 | 2016-10-14 | 7375 | [8 empty] | 7375 | 5 |  |  |  |  | 7375
77.7 | SRF Reserve B Loan | 5 | 2016-10-19 | 822 | [8 empty] | 822 | 5 |  |  |  |  | 822
79 | Accounting Adjustment |  |  | 0.1 | [10 empty] | 0.1 |  |  |  | 0.1
80 | Great West Engineering (Grant Administration) | 15516 | 2016-10-27 | 4308.5 | [8 empty] | 4309 | 6 |  |  |  |  | 4309
81 | Great West Engineering (Thompson Well Replacement) | 15514 | 2016-10-27 | 38.5 | [6 empty] | 39 | 6 | [6 empty] | 39
82 | Great West Engineering (Construction Management) | 15514 | 2016-10-27 | 9383.66 | [6 empty] | 9384 | 6 | [6 empty] | 9384
83 | Great West Engineering (Resident Project Representative) | 15514 | 2016-10-27 | 23442.32 | [6 empty] | 23442 | 6 | [6 empty] | 23442
84 | Battle Ridge Builders, LLC | 5 | 2016-10-31 | 237363.82 |  |  | 237363.82 | 4 | [10 empty] | 237363.82
85 | SRF Reserve B Loan | 6 | 2016-11-02 | 164 | [8 empty] | 164 | 6 |  |  |  |  | 164
86 | Great West Engineering (Grant Administration) | 15594 | 2016-11-17 | 2541.32 | [6 empty] | 2541 | 7 | [6 empty] | 2541
87 | Great West Engineering (Construction Management) | 15600 | 2016-11-17 | 10384.3 | [10 empty] | 10384.3 | 4 |  |  | 10384.3
88 | Great West Engineering (Resident Project Representative) | 15600 | 2016-11-17 | 21131.73 | [10 empty] | 21131.73 | 4 |  |  | 21131.73
89 | Battle Ridge Builders, LLC | 6 | 2016-12-05 | 249309.45 |  |  | 249309.45 | 5 | [10 empty] | 249309.45
90 | Central Lumber | 73685 | 2016-10-25 | 32.64 |  |  | 32.64 | 5 | [10 empty] | 32.64
91 | Battle Ridge Builders, LLC | 7 | 2016-12-21 | 30773.98 |  |  | 30773.98 | 6 | [10 empty] | 30773.98
92 | Great West Engineering (Grant Administration) | 15686 | 2016-12-21 | 1995.5 | [8 empty] | 1996 | 7 |  |  |  |  | 1996
93 | Great West Engineering (Construction Management) | 15723 | 2016-12-23 | 7998.1 | [10 empty] | 7998.1 | 5 |  |  | 7998.1
94 | Great West Engineering (Resident Project Representative) | 15723 | 2016-12-23 | 9265.44 | [8 empty] | 2819 | 7 | 6446.44 | 5 |  |  | 9265.44
95 | SRF Reserve B Loan | 7 | 2017-01-03 | 182.97 | [8 empty] | 183 | 7 |  |  |  |  | 183
96 | Great West Engineering (Grant Administration) | 15856 | 2017-01-25 | 1262.5 | [8 empty] | 1262 | 8 |  |  |  |  | 1262
97 | Great West Engineering (Construction Management) | 15857 | 2017-01-25 | 3317 | [10 empty] | 3317 | 6 |  |  | 3317
98 | SRF Reserve B Loan | 8 | 2017-02-06 | 48 | [8 empty] | 48 | 8 |  |  |  |  | 48
99 | Great West Engineering (Grant Administration) | 15892 | 2017-02-21 | 896.75 | [8 empty] | 897 | 9 |  |  |  |  | 897
100 | Great West Engineering (Grant Administration) | 15893 | 2017-02-21 | 610.5 | [8 empty] | 610 | 9 |  |  |  |  | 610
101 | Mahurin Excavating & Drilling (Pritchard Well) | 2 | 2017-02-14 | 7900 | [8 empty] | 7900 | 9 |  |  |  |  | 7900
102 | Mahurin Excavating & Drilling (Pritchard Well) | 3 | 2017-02-22 | 1381 | [8 empty] | 1381 | 9 |  |  |  |  | 1381
103 | SRF Reserve B Loan | 9 | 2017-03-08 | 410 | [8 empty] | 410 | 9 |  |  |  |  | 410
104 | Great West Engineering (Grant Administration) | 16007 | 2017-03-20 | 778.75 | [8 empty] | 779 | 10 |  |  |  |  | 779
105 | Nash Electric | 1408 | 2017-02-15 | 595 | [8 empty] | 595 | 10 |  |  |  |  | 595
106 | Nash Electric | 1409 | 2017-02-15 | 209 | [8 empty] | 209 | 10 |  |  |  |  | 209
107 | SRF Reserve B Loan | 10 | 2017-03-27 | 60 | [8 empty] | 60 | 10 |  |  |  |  | 60
108 | Great West Engineering (Construction Management) | 16148 | 2017-04-17 | 756 | [6 empty] | 756 | 8 | [6 empty] | 756
109 | Great West Engineering (Grant Administration) | 16115 | 2017-04-17 | 264.5 | [6 empty] | 254 | 8 | [6 empty] | 254
110 | Great West Engineering (Grant Administration) | 16241 | 2017-05-23 | 111 | [6 empty] | 111 | 8 | [6 empty] | 111
111 | Great West Engineering (Construction Management) | 16253 | 2017-05-23 | 252 | [6 empty] | 252 | 8 | [6 empty] | 252
112 | Great West Engineering (Grant Administration) | 16373 | 2017-06-20 | 527.25 | [6 empty] | 527 | 8 | [6 empty] | 527
113 | Battle Ridge Builders, LLC | 8 | 2017-06-23 | 139048.17 |  |  | 37069.66 | 7 | 8051.4 | 4 | 4154 | 8 | 62393 | 11 | 20613.94 | 7 | 6766.17 | 1 | 139048.17
114 | DIS Tech * | 30372 | 2016-10-06 | 948.6 |  |  |  |  | 948.6 | 4 | [8 empty] | 948.6
115 | SRF Reserve B Loan | 10 | 2017-07-13 | 1711.21 | [8 empty] | 1711 | 11 |  |  |  |  | 1711
116 | Wilting Plumbing and Heating (Meters) | 2 | 2018-10-18 | 28732.5 | [8 empty] | 26882 | 12 | 1850.4 | 8 |  |  | 28732.4
117 | Northwest Pipe Fitting (Water Meters) | 134481 | 2018-10-17 | 667.5 | [8 empty] | 668 | 12 |  |  |  |  | 668
118 | [18 empty] | 0
119 | [18 empty] | 0
120 | [18 empty] | 0 | SRF B
121 | [18 empty] | 0 | 27550
122 | [18 empty] | 0 | WRDA
123 | [18 empty] | 0 | 1850.4
124 | [18 empty] | 0 | Total
| Copy and submit to the applicable funding agency with each drawdown request. |  |  | 2231774.56 |  |  | 750000 |  | 450000 |  | 392500 |  | 392500 |  | 240000 |  | 6766.17 |  | 2231766.17 | 29400.4
| uniblank.xls | [7 empty] | 0
* The total DIS Tech invoice #30372 was $1,897.20. Half the invoice, $948.60, was paid with TSEP Draw Request #3. The remaining amount on the invoice, $948.60 is requested from CDBG Draw Request #4

## Sheet1
| UNIFORM INVOICE TRACKING SPREADSHEET FOR: DATE: | City of Harlowton Phase II Water System Improvements | [6 empty] | Date: |  | 2019-01-09 16:08
| Vendor's Name | Invoice or Pay Estimate Number | Invoice Date or Time Period Covered | Total Amount of Invoice | Warrant Number | Date Paid | Funding Source, Amount Expended, Drawdown Number | [8 empty] | Total Amount Paid This Invoice | WRDA 75/25 Split
[7 empty] | Funding Source: |  | Funding Source: |  |  | Funding Source:
IT# | [6 empty] | SRF A Loan | # | SRF B Loan | # |  |  | # |  |  |  | WRDA | Local
94 | 1% Gross Receipts Tax | 1 | 2013-08-05 | 179.63 |  |  | 179.63 | 4 | [7 empty] | 179.63
102 | 1% Gross Receipts Tax | 2 | 2013-10-15 | 167.57 |  |  | 167.57 | 6 | [7 empty] | 167.57
47 | Adjusting Entry (Rounding) |  |  | 4.28 |  |  | 0 |  | 4.28 | 1 |  | 0 |  |  |  | 4.28 | 3.21 | 1.07 | 4.28
43 | Central Lumber | 45439 | 2013-04-16 | 116.04 |  |  | 0 |  | 116.04 | 1 |  | 0 |  |  |  | 116.04 | 87.03 | 29.01 | 116.04
6 | Dorsey & Whitney | 1828330 | 2012-10-26 | 2000 |  |  | 2000 | 1 | 0 |  |  | 0 |  |  |  | 2000 | 1500 | 500 | 2000 | 206.25
86 | Dorsey & Whitney | 1889165 | 2013-07-25 | 8000 |  |  | 2000 | 3 | 6000 | 3 | [5 empty] | 8000
75 | Duncan Ranch Colony (Cement) | 1 | 2013-08-13 | 385 |  |  | 385 | 2 | 0 | [6 empty] | 385
44 | Ferguson Enterprises, Inc | 574296 | 2013-04-03 | 148.62 |  |  | 0 |  | 148.62 | 1 |  | 0 |  |  |  | 148.62 | 111.465 | 37.155 | 148.62 |  |  |  | 0
45 | Ferguson Enterprises, Inc | 575120 | 2013-04-15 | 108.56 |  |  | 0 |  | 108.56 | 1 |  | 0 |  |  |  | 108.56 | 81.42 | 27.14 | 108.56
51 | Ferguson Enterprises, Inc | 574393 | 2013-04-03 | 2156.58 |  |  | 2156.58 | 1 | 0 | [6 empty] | 2156.58
52 | Ferguson Enterprises, Inc | 575042 | 2013-04-15 | 356.01 |  |  | 356.01 | 1 | 0 | [6 empty] | 356.01
53 | Ferguson Enterprises, Inc | 575396-1 | 2013-04-24 | 229.94 |  |  | 229.94 | 1 | 0 | [6 empty] | 229.94 | 172.455 | 57.485 | 229.94
54 | Ferguson Enterprises, Inc | 575498 | 2013-04-30 | 325.2 |  |  | 325.2 | 1 | 0 | [6 empty] | 325.2
55 | Ferguson Enterprises, Inc | 576152 | 2013-05-07 | 25 |  |  | 25 | 1 | 0 | [6 empty] | 25
56 | Ferguson Enterprises, Inc | 576256 | 2013-05-08 | 89.62 |  |  | 89.62 | 1 | 0 | [6 empty] | 89.62
57 | Ferguson Enterprises, Inc | 576423 | 2013-05-10 | 1142.81 |  |  | 1142.81 | 1 | 0 | [6 empty] | 1142.81
58 | Ferguson Enterprises, Inc | 576070 | 2013-05-20 | 17846.37 |  |  | 17846.37 | 1 | 0 | [6 empty] | 17846.37
59 | Ferguson Enterprises, Inc | 576033 | 2013-05-20 | 788.26 |  |  | 788.26 | 1 | 0 | [6 empty] | 788.26
33 | Great West Engineeering (Pritchard Well Testing & Report) | 10791 | 2013-04-22 | 19335.91 | 1058 | 2013-05-30 | 19335.91 | 1 | 0 |  |  | 0 |  |  |  | 19335.91 | 14501.9325 | 4833.9775 | 19335.91
39 | Great West Engineeering (Pritchard Well Testing & Report) | 10899 | 2013-05-23 | 6198.22 | 1070 | 2013-08-09 | 6198.22 | 1 | 0 |  |  | 0 |  |  |  | 6198.22 | 4648.665 | 1549.555 | 6198.22
8 | Great West Engineering (Bidding) | 10340 | 2012-10-30 | 485 | 1048 | 2012-11-07 | 485 | 1 | 0 |  |  | 0 |  |  |  | 485 | 363.75 | 121.25 | 485 | 82.5
12 | Great West Engineering (Bidding) | 10397 | 2012-11-21 | 658.5 | 1053 | 2012-11-11 | 658.5 | 1 | 0 |  |  | 0 |  |  |  | 658.5 |  | 164.625 | 164.625
18 | Great West Engineering (Bidding) | 10547 | 2013-01-22 | 140 | 1055 | 2013-03-07 | 140 | 1 | 0 |  |  | 0 |  |  |  | 140 | 105 | 35 | 140 | 103.13
21 | Great West Engineering (Bidding) | 10637 | 2013-02-20 | 212 | 1056 | 2013-04-15 | 212 | 1 | 0 |  |  | 0 |  |  |  | 212 | 159 | 53 | 212 | 309.18
26 | Great West Engineering (Bidding) | 10723 | 2013-03-19 | 965.75 | 1056 | 2013-04-15 | 965.75 | 1 | 0 |  |  | 0 |  |  |  | 965.75 |  | 241.4375 | 241.4375
29 | Great West Engineering (Bidding) | 10791 | 2013-04-22 | 3972.16 | 1058 | 2013-05-30 | 3972.16 | 1 | 0 |  |  | 0 |  |  |  | 3972.16 | 2979.12 | 993.04 | 3972.16 | 15000
35 | Great West Engineering (Bidding) | 10899 | 2013-05-23 | 4440.08 | 1070 | 2013-08-09 | 4440.08 | 1 | 0 |  |  | 0 |  |  |  | 4440.08 | 3330.06 | 1110.02 | 4440.08
77 | Great West Engineering (Bidding) | 11119 | 2013-07-29 | 712.07 | 1073 | 2013-09-10 | 712.07 | 2 | 0 | [6 empty] | 712.07
87 | Great West Engineering (Bidding) | 11186 | 2013-08-21 | 1267.86 | 1077 | 2013-10-03 | 1267.86 | 3 | [7 empty] | 1267.86
15 | Great West Engineering (Construction Management) | 10476 | 2012-12-18 | 532.5 | 1054 | 2013-01-29 | 532.5 | 1 | 0 |  |  | 0 |  |  |  | 532.5 |  | 133.125 | 133.125
30 | Great West Engineering (Construction Management) | 10791 | 2013-04-22 | 381.75 | 1058 | 2013-05-30 | 381.75 | 1 | 0 |  |  | 0 |  |  |  | 381.75 |  | 95.4375 | 95.4375
36 | Great West Engineering (Construction Management) | 10899 | 2013-05-23 | 986.2 | 1070 | 2013-08-09 | 986.2 | 1 | 0 |  |  | 0 |  |  |  | 986.2 | 739.65 | 246.55 | 986.2
61 | Great West Engineering (Construction Management) | 10951 | 2013-06-18 | 2191.21 | 1073 | 2013-10-09 | 2191.21 | 1 | 0 | [6 empty] | 2191.21
78 | Great West Engineering (Construction Management) | 11119 | 2013-07-29 | 4721.35 | 1073 | 2013-09-10 | 4721.35 | 2 | 0 | [6 empty] | 4721.35
88 | Great West Engineering (Construction Management) | 11186 | 2013-08-21 | 2666.3 | 1077 | 2013-10-03 | 2666.3 | 3 | [7 empty] | 2666.3
95 | Great West Engineering (Construction Management) | 11290 | 2013-09-25 | 3077 | 1081 | 2013-10-21 | 3077 | 5 | [7 empty] | 3077
103 | Great West Engineering (Construction Management) | 11417 | 2013-10-22 | 3572.84 |  |  | 1978.38 | 6 | 1594.46 | 4 | [5 empty] | 3572.84 | [5 empty] | SRF B Loan
106 | Great West Engineering (Construction Management) | 11568 | 2013-11-21 | 2831 |  |  |  |  | 2831 | 5 | [5 empty] | 2831 | [5 empty] | 0
109 | Great West Engineering (Construction Management) | 11627 | 2013-12-17 | 60.5 |  |  |  |  | 60.5 | [6 empty] | 60.5
112 | Great West Engineering (Construction Management) | 11779 | 2014-01-24 | 336.5 |  |  |  |  | 336.5 | [6 empty] | 336.5
114 | Great West Engineering (Construction Management) | 11844 | 2014-02-19 | 292 |  |  |  |  | 292 | [6 empty] | 292
1 | Great West Engineering (Design) | 9962 | 2012-07-24 | 5905.4 | 1048 | 2012-11-07 | 5905.4 | 1 | 0 |  |  | 0 |  |  |  | 5905.4 | #REF! | #REF! | #REF! | 262.5 |  |  | #REF!
3 | Great West Engineering (Design) | 10068 | 2012-08-21 | 21747.86 | 1048 | 2012-11-07 | 21747.86 | 1 | 0 |  |  | 0 |  |  |  | 21747.86 | 4429.05 | 1476.35 | 5905.4 | 37.5 |  |  | #REF!
4 | Great West Engineering (Design) | 10162 | 2012-09-18 | 9289.54 | 1048 | 2012-11-07 | 9289.54 | 1 | 0 |  |  | 0 |  |  |  | 9289.54 | 6967.155 | 2322.385 | 9289.54 | 178.13
7 | Great West Engineering (Design) | 10340 | 2012-10-30 | 3821 | 1048 | 2012-11-07 | 3821 | 1 | 0 |  |  | 0 |  |  |  | 3821 | 2865.75 | 955.25 | 3821 | 969.38
11 | Great West Engineering (Design) | 10397 | 2012-11-21 | 499.75 | 1053 | 2012-11-11 | 499.75 | 1 | 0 |  |  | 0 |  |  |  | 499.75 | 374.8125 | 124.9375 | 499.75 | 108.75
14 | Great West Engineering (Design) | 10476 | 2012-12-18 | 396.25 | 1054 | 2013-01-29 | 396.25 | 1 | 0 |  |  | 0 |  |  |  | 396.25 | 297.1875 | 99.0625 | 396.25 | 546
17 | Great West Engineering (Design) | 10547 | 2013-01-22 | 632.5 | 1055 | 2013-03-07 | 632.5 | 1 | 0 |  |  | 0 |  |  |  | 632.5 |  | 158.125 | 158.125
20 | Great West Engineering (Design) | 10637 | 2013-02-20 | 2223 | 1056 | 2013-04-15 | 2223 | 1 | 0 |  |  | 0 |  |  |  | 2223 |  | 555.75 | 555.75
25 | Great West Engineering (Design) | 10723 | 2013-03-19 | 1650.96 | 1056 | 2013-04-15 | 1650.96 | 1 | 0 |  |  | 0 |  |  |  | 1650.96 | 1238.22 | 412.74 | 1650.96 | 4132.13
28 | Great West Engineering (Design) | 10791 | 2013-04-22 | 1228.5 | 1058 | 2013-05-30 | 1228.5 | 1 | 0 |  |  | 0 |  |  |  | 1228.5 |  | 307.125 | 307.125
34 | Great West Engineering (Design) | 10899 | 2013-05-23 | 104 | 1070 | 2013-08-09 | 104 | 1 | 0 |  |  | 0 |  |  |  | 104 | 78 | 26 | 104
60 | Great West Engineering (Design) | 10951 | 2013-06-18 | 10740.75 | 1073 | 2013-10-09 | 10740.75 | 1 | 0 | [6 empty] | 10740.75
76 | Great West Engineering (Design) | 11119 | 2013-07-29 | 5628 | 1073 | 2013-09-10 | 5628 | 2 | 0 | [6 empty] | 5628
5 | Great West Engineering (Grant Administration) | 10162 | 2012-09-18 | 790.5 | 1048 | 2012-11-07 | 790.5 | 1 | 0 |  |  | 0 |  |  |  | 790.5 | 592.875 | 197.625 | 790.5 | 165
9 | Great West Engineering (Grant Administration) | 10340 | 2012-10-30 | 1015 | 1048 | 2012-11-07 | 1015 | 1 | 0 |  |  | 0 |  |  |  | 1015 |  | 253.75 | 253.75
13 | Great West Engineering (Grant Administration) | 10397 | 2012-11-21 | 584.75 | 1053 | 2012-11-11 | 584.75 | 1 | 0 |  |  | 0 |  |  |  | 584.75 | 438.5625 | 146.1875 | 584.75 | 1715.03
16 | Great West Engineering (Grant Administration) | 10476 | 2012-12-18 | 320.75 | 1054 | 2013-01-29 | 320.75 | 1 | 0 |  |  | 0 |  |  |  | 320.75 | 240.5625 | 80.1875 | 320.75 | 946.01
19 | Great West Engineering (Grant Administration) | 10547 | 2013-01-22 | 280 | 1055 | 2013-03-07 | 280 | 1 | 0 |  |  | 0 |  |  |  | 280 | 210 | 70 | 280 | 1549.9
22 | Great West Engineering (Grant Administration) | 10637 | 2013-02-20 | 497.5 | 1056 | 2013-04-15 | 497.5 | 1 | 0 |  |  | 0 |  |  |  | 497.5 | 373.125 | 124.375 | 497.5 | 330
27 | Great West Engineering (Grant Administration) | 10723 | 2013-03-19 | 172.25 | 1056 | 2013-04-15 | 172.25 | 1 | 0 |  |  | 0 |  |  |  | 172.25 | 129.1875 | 43.0625 | 172.25 | 3369
32 | Great West Engineering (Grant Administration) | 10791 | 2013-04-22 | 493.75 | 1058 | 2013-05-30 | 493.75 | 1 | 0 |  |  | 0 |  |  |  | 493.75 | 370.3125 | 123.4375 | 493.75 | 330
38 | Great West Engineering (Grant Administration) | 10899 | 2013-05-23 | 381.75 | 1070 | 2013-08-09 | 248.46 | 1 | 133.29 | 1 |  | 0 |  |  |  | 381.75 | 286.3125 | 95.4375 | 381.75
63 | Great West Engineering (Grant Administration) | 10951 | 2013-06-18 | 915.5 | 1073 | 2013-10-09 | 915.5 | 1 | 0 | [6 empty] | 915.5
80 | Great West Engineering (Grant Administration) | 11119 | 2013-07-29 | 866.1 | 1073 | 2013-09-10 | 866.1 | 2 | 0 | [6 empty] | 866.1
90 | Great West Engineering (Grant Administration) | 11186 | 2013-08-21 | 457.25 | 1077 | 2013-10-03 | 15.44 | 3 | 441.81 | [6 empty] | 457.25
97 | Great West Engineering (Grant Administration) | 11290 | 2013-09-25 | 660.91 | 1081 | 2013-10-21 | 660.91 | 5 | [7 empty] | 660.91
104 | Great West Engineering (Grant Administration) | 11417 | 2013-10-22 | 612.5 |  |  | 612.5 | 6 | [7 empty] | 612.5 | [5 empty] | 3440.41
107 | Great West Engineering (Grant Administration) | 11568 | 2013-11-21 | 356.25 |  |  |  |  | 356.25 | 5 | [5 empty] | 356.25
111 | Great West Engineering (Grant Administration) | 11627 | 2013-12-17 | 286.75 |  |  | 286.75 | 7 | [7 empty] | 286.75
113 | Great West Engineering (Grant Administration) | 11779 | 2014-01-24 | 129.37 |  |  | 129.37 | 7 | [7 empty] | 129.37
115 | Great West Engineering (Grant Administration) | 11844 | 2014-02-19 | 179 |  |  | 179 | 7 | [7 empty] | 179
8999.88
110 | Great West Engineering (Post Construction) | 11627 | 2013-12-17 | 1435.25 |  |  |  |  | 1435.25 | [6 empty] | 1435.25
2 | Great West Engineering (Pritchard Well Testing & Report) | 9962 | 2012-07-24 | 3899.5 | 1048 | 2012-11-07 | 3899.5 | 1 | 0 |  |  | 0 |  |  |  | 3899.5 | #REF! | #REF! | #REF! | 896.25
10 | Great West Engineering (Pritchard Well Testing & Report) | 10340 | 2012-10-30 | 68 | 1048 | 2012-11-07 | 68 | 1 | 0 |  |  | 0 |  |  |  | 68 | 51 | 17 | 68 | 20.63
91 | Great West Engineering (Pritchard Well Testing & Report) | 11186 | 2013-08-21 | 458.08 | 1077 | 2013-10-03 | 458.08 | 3 | [7 empty] | 458.08
98 | Great West Engineering (Pritchard Well Testing & Report) | 11290 | 2013-09-25 | 50.49 | 1081 | 2013-10-21 | 50.49 | 5 | [7 empty] | 50.49
31 | Great West Engineering (Resident Project Rep) | 10791 | 2013-04-22 | 2103.35 | 1058 | 2013-05-30 | 2103.35 | 1 | 0 |  |  | 0 |  |  |  | 2103.35 | 1577.5125 | 525.8375 | 2103.35
37 | Great West Engineering (Resident Project Rep) | 10899 | 2013-05-23 | 1962 | 1070 | 2013-08-09 | 1962 | 1 | 0 |  |  | 0 |  |  |  | 1962 | 1471.5 | 490.5 | 1962
79 | Great West Engineering (Resident Project Rep) | 11119 | 2013-07-29 | 8690.88 | 1073 | 2013-09-10 | 8690.88 | 2 | 0 | [6 empty] | 8690.88
89 | Great West Engineering (Resident Project Rep) | 11186 | 2013-08-21 | 15230.1 | 1077 | 2013-10-03 | 15230.1 | 3 | [7 empty] | 15230.1
96 | Great West Engineering (Resident Project Rep) | 11290 | 2013-09-25 | 4631.55 | 1081 | 2013-10-21 | 4631.55 | 5 | [7 empty] | 4631.55
62 | Great West Enginering (RPR) | 10951 | 2013-06-18 | 6197.3 | 1073 | 2013-10-09 | 6197.3 | 1 | 0 | [6 empty] | 6197.3
48 | Harlowton Labor Costs - Charged to Construction in April | 1 | 2013-07-02 | 9029.76 |  |  | 9029.76 | 1 | 0 |  |  | 0 |  |  |  | 9029.76 | 6772.32 | 2257.44 | 9029.76
65 | Harlowton Labor Costs - Charged to Construction in June | 3 | 2012-07-31 | 7456.73 |  |  | 7456.73 | 2 | 0 | [6 empty] | 7456.73
49 | Harlowton Labor Costs - Charged to Construction in May | 2 | 2013-07-02 | 10281.13 |  |  | 10281.13 | 1 | 0 | [6 empty] | 10281.13
23 | HD Supply Water Works | 6148710 | 2013-02-28 | 14792.41 |  |  | 8594.19 | 1 | 6198.22 |  |  | 0 |  |  |  | 14792.41 | 11094.3075 | 3698.1025 | 14792.41 | 3458.18 |  |  | 444291.87
40 | HD Supply Water Works | 6148713 | 2013-02-28 | 14792.41 |  |  | 0 |  | 14792.41 | 1 |  | 0 |  |  |  | 14792.41 | 11094.3075 | 3698.1025 | 14792.41 |  | 14964.66
41 | HD Supply Water Works | 6534378 | 2013-04-25 | -1645.35 |  |  | 0 |  | -1645.35 | 1 |  | 0 |  |  |  | -1645.35 | -1234.0125 | -411.3375 | -1645.35
93 | Mahurin Excavation & Drilling | 1 | 2013-08-05 | 17782.87 |  |  | 17782.87 | 4 | [7 empty] | 17782.87
101 | Mahurin Excavation & Drilling | 2 | 2013-10-15 | 16589.93 |  |  | 16589.93 | 6 | [7 empty] | 16589.93 | [5 empty] | SRF A Loan
66 | Martin Excavation | 539 | 2013-06-06 | 17310 |  |  | 17310 | 2 | 0 | [6 empty] | 17310
67 | Martin Excavation | 540 | 2013-06-06 | 15010 |  |  | 15010 | 2 | 0 | [6 empty] | 15010
68 | Martin Excavation | 542 | 2013-07-10 | 15281.5 |  |  | 15281.5 | 2 | 0 | [6 empty] | 15281.5
82 | MT Dept of Revenue | 1 | 2013-07-26 | 1164.69 |  |  | 0 |  | 1164.69 | 2 | [5 empty] | 1164.69
85 | MT Dept of Revenue | 2 | 2013-09-05 | 2415.2 |  |  | 2415.2 | 3 | [7 empty] | 2415.2
100 | MT Dept of Revenue | 3 | 2013-09-23 | 188.42 |  |  | 188.42 | 5 | [7 empty] | 188.42
81 | Phillips Construction | 1 | 2013-07-26 | 115303.89 |  |  | 0 |  | 115303.89 | 2 | [5 empty] | 115303.89
84 | Phillips Construction | 2 | 2013-09-05 | 239105.01 |  |  | 39842.77 | 3 | 199262.24 | 3 | [5 empty] | 239105.01
99 | Phillips Construction | 3 | 2013-09-23 | 18653.09 |  |  | 18653.09 | 5 | [7 empty] | 18653.09
42 | Remedies Pharmacy & Hardware | 53220 | 2013-04-24 | 6.98 |  |  | 0 |  | 6.98 | 1 |  | 0 |  |  |  | 6.98 | 5.235 | 1.745 | 6.98
69 | Remedies Pharmacy & Hardware | 56909 | 2013-06-07 | 5.95 |  |  | 5.95 | 2 | 0 | [6 empty] | 5.95
70 | Remedies Pharmacy & Hardware | 57956 | 2013-06-18 | 36.38 |  |  | 36.38 | 2 | 0 | [6 empty] | 36.38
71 | Remedies Pharmacy & Hardware | 57960 | 2013-06-18 | 31.14 |  |  | 31.14 | 2 | 0 | [6 empty] | 31.14
72 | Remedies Pharmacy & Hardware | 58050 | 2013-06-19 | 2.98 |  |  | 2.98 | 2 | 0 | [6 empty] | 2.98
73 | Remedies Pharmacy & Hardware | 58082 | 2013-06-19 | 1.49 |  |  | 1.49 | 2 | 0 | [6 empty] | 1.49
74 | Remedies Pharmacy & Hardware | 58625 | 2013-06-25 | 4.69 |  |  | 4.69 | 2 | 0 | [6 empty] | 4.69
24 | Spring Water Colony (Bedding Material) |  | 2013-03-13 | 34300 |  |  | 34300 | 1 | 0 |  |  | 0 |  |  |  | 34300 | 25725 | 8575 | 34300 | 491.25
46 | SRF BAN Loan Interest | 1 | 2013-07-25 | 762.53 |  |  | 0 |  | 762.53 | 1 |  | 0 |  |  |  | 762.53 | 571.8975 | 190.6325 | 762.53
64 | SRF Loan Reserves | 1 | 2013-07-25 | 1638.32 |  |  | 0 |  | 1638.32 | 1 | [5 empty] | 1638.32
83 | SRF Loan Reserves | 2 | 2013-08-13 | 9251.1 |  |  | 0 |  | 9251.1 | 2 | [5 empty] | 9251.1
92 | SRF Loan Reserves | 3 | 2013-09-10 | 10796 |  |  |  |  | 10796 | 3 | [5 empty] | 10796
105 | SRF Loan Reserves | 4 | 2013-11-12 | 126.65 |  |  |  |  | 126.65 | 4 | [5 empty] | 126.65 | [5 empty] | Total
108 | SRF Loan Reserves | 5 |  | 253.16 |  |  |  |  | 253.16 | 5 | [5 empty] | 253.16
50 | Stitchin' Dreams Embroidery | 5680 | 2013-05-13 | 25.27 |  |  | 25.27 | 1 | 0 | [6 empty] | 25.27
116 | [15 empty] | 0
| Copy and submit to the applicable funding agency with each drawdown request. |  | TOTALS | 791454.29 |  |  | 410685.01 |  | 371769.4 |  | 0 | 0 |  | 0 | 0 | 782454.41 | #REF! | 197863.5725 | #REF!
uniblank.xls
8999.88

## Sheet2
12
473
Great West Engineering (Post Construction) | 11627 | 2013-12-17 | 1435.25 |  |  | 1435.25 | 5 |  |  | 1435.25
Great West Engineering (Construction Management) | 11568 | 2013-11-21 | 2831 |  |  | 2831 | 5 |  |  | 2831
Great West Engineering (Construction Management) | 11627 | 2013-12-17 | 60.5 |  |  | 60.5 | 5 |  |  | 60.5
Great West Engineering (Construction Management) | 11779 | 2014-01-24 | 105 |  |  | 105 | 5 |  |  | 105 | 3134.48
Great West Engineering (Construction Management) | 11844 | 2014-02-19 | 292 |  |  | 292 | 5 |  |  | 292 | SRF B Loan
Great West Engineering (Construction Management) | 11950 | 2014-03-18 | 2534.5 |  |  | 2534.5 | 5 | 7258.25 | 8853 | 2534.5 | 3134.48
Great West Engineering (Construction Management) | 12055 | 2014-04-23 | 2810.6 |  |  | 2810.6 | 5 | 2810.6 | 2810.6 | 2810.6
[6 empty] | 10068.85 |  | 10068.85 | 11663.6
Great West Engineering (Grant Administration) | 11568 | 2013-11-21 | 356.25 | 356.25 | 7 |  |  |  |  | 356.25
Great West Engineering (Grant Administration) | 11627 | 2013-12-17 | 286.75 | 286.75 | 7 |  |  |  |  | 286.75
Great West Engineering (Grant Administration) | 11779 | 2014-01-24 | 336.5 |  |  | 336.5 | 5 | 763 | 8996 | 336.5 | SRF A Loan
Great West Engineering (Grant Administration) | 11844 | 2014-02-19 | 179 |  |  | 179 | 5 | 437.27 | 437.27 | 179 | 46988.47
Great West Engineering (Grant Administration) | 11950 | 2014-03-18 | 247.5 |  |  | 247.5 | 5 | 1200.27 | 9433.27 | 247.5
Great West Engineering (Grant Administration) | 12055 | 2014-04-23 | 519.75 | 82.48 |  | 437.27 | 5 |  |  | 519.75
|  |  |  | 725.48 |  | 1200.27 |  |  | 9433.27
Mahurin Excavation & Drilling (Pritchard Well Completion & Column Pipe) | 1 | 2014-02-24 | 30400 | 1683.52 | 7 | 28716.48 | 5 |  |  | 30400 | Total